## Sheet1
				Green Light					end
	SCHEDULE			planning			work					work				winter break					Kick off					First stage review					end
				13/12/21					20/12/21					27/12/21					03/01/22					10/01/22					17/01/22					24/01/22					31/01/22					07/02/22					14/02/22					21/02/22					28/02/22					07/03/22					14/03/22					21/03/22					28/03/22					04/04/22					11/04/22					18/04/22					25/04/22					02/05/22					09/05/22					16/05/22					23/05/22					30/05/22					06/06/22					13/06/22					20/06/22					27/06/22					04/07/22					11/07/22					18/07/22					25/07/22					end
	TASK	PROGRESS		13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	end
				M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	end
	Start writing					end
	Create outline	0.00%					end
				end
	Reproduce results					end
	Creating indexes					end
	Create Elasticsearch index as in ‘Fair Ranking in Academic Search’, by Malte Bonart	95.00%					end
	Create Terrier index as in “McDonald and Ounis, ‘University of Glasgow Terrier Team at the TREC 2020Fair Ranking Track’.”	0.00%					end
				end
	Reproduce results for each of the following approaches:					end
	Term weighting (2020)	0.00%					end
	Plackett-Luce sampler (2020)	0.00%					end
	Controller (2020)	0.00%					end
	Data fusion (2020)	0.00%					end
	Pairwise LTR (2020)	0.00%					end
	Listwise LTR (2020)	0.00%					end
	Dissimilarity (2020)	0.00%					end
	Cost function (2020)	0.00%					end
	Pairwise LTR (2019)	90.00%					end
	Greedy algorithm (2019)	0.00%					end
	Diversification (2019)	0.00%					end
	Random shuffle (2019)	100.00%					end
	Term weighting (2019)	0.00%					end
				end
	Design toy example	0.00%					end
	Describe individual approaches (write parallel with reproduction steps)					end
	Write a couple paragraphs on why these approaches, how they were selected (methodology)	0.00%					end
	Write specific implementation details for each approach (appendix)	0.00%					end
	Write description dataset, indexing steps, any stemming etc (methodology)	0.00%					end
	Write down which approaches we selected in the end and how they performed on the dataset (experiments)	0.00%					end
				end
	Error analysis					end
	Determine how to perform error analysis on sequence of rankings					end
	Write 1-2 paragraphs on how to perform error analysis on a sequence of queries (methodology)					end
				end
	Perform error analysis for each of the implemented approaches:					end
	Term weighting (2020)	0.00%					end
	Plackett-Luce sampler (2020)	0.00%					end
	Controller (2020)	0.00%					end
	Data fusion (2020)	0.00%					end
	Pairwise LTR (2020)	0.00%					end
	Listwise LTR (2020)	0.00%					end
	Dissimilarity (2020)	0.00%					end
	Cost function (2020)	0.00%					end
	Pairwise LTR (2019)	0.00%					end
	Greedy algorithm (2019)	0.00%					end
	Diversification (2019)	0.00%					end
	Random shuffle (2019)	0.00%					end
	Term weighting (2019)	0.00%					end
				end
	Write error analysis section – discuss individual results and draw overarching conclusions to support the choice of improvement later					end
				end
				end
				end
				end
	Propose improvement					end
	Write literature review on causal fairness in ML as a whole					end
	Write literature review on causal fairness in ranking specifically					end
				end
	Based on literature and error analysis of previous years, propose a different ranking method that will hopefully work better					end
				end
	Implement improvement					end
	Implement code to create fair ranking					end
	Write implementation details in appendix					end
	Write idea behind implementation in its own section					end
				end
	Evaluate improvement					end
	Create runs with improved algorithm					end
	Evaluate runs with 2019 & 2020 metrics					end
	Do error analysis on improved runs					end
				end
	Write discussion on error analysis and overall outcomes. Did our approach improve upon previous results? Can we explain why/why not? Do we propose remedies for what we see?					end
				end
	Write the final version					end
	Finish up drafts of methodology, experiments, etc.					end
	Write background (all information that hasn’t been mentioned yet but is still relevant) draft					end
	Write abstract draft					end
	Write introduction draft					end
	Write conclusion draft					end

	Write background final					end
	Write methodology final					end
	Write experiments final					end
	Write error analysis of previous approaches final					end
	Write proposed improvement final					end
	Write experiments proposed improvement final					end
	Write error analysis proposed improvement final					end
	Write discussion final					end
	Write implementation details (appendix) final					end
				end
	Write abstract final					end
	Write introduction final					end
	Write conclusion final					end
				end
	Presentation					end
	Whittle down thesis to the key ingredients					end
	Pour the key ingredients into a presentation					end
end	end	end	end	end	end	end	end	end	end	end