## Sheet1
				Green Light					end
	SCHEDULE			planning			work					work				winter break					Kick off					First stage review					end
				13/12/21					20/12/21					27/12/21					03/01/22					10/01/22					17/01/22					24/01/22					31/01/22					07/02/22					14/02/22					21/02/22					28/02/22					07/03/22					14/03/22					21/03/22					28/03/22					04/04/22					11/04/22					18/04/22					25/04/22					02/05/22					09/05/22					16/05/22					23/05/22					30/05/22					06/06/22					13/06/22					20/06/22					27/06/22					04/07/22					11/07/22					18/07/22					25/07/22					end
	TASK	PROGRESS		13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	end
				M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	end
	Start writing					end
	Create outline	100.00%					end
				end
	Reproduce results					end
	Creating indexes					end
	Create Elasticsearch index as in ‘Fair Ranking in Academic Search’, by Malte Bonart	100.00%					end
	Create Terrier index as in “McDonald and Ounis, ‘University of Glasgow Terrier Team at the TREC 2020Fair Ranking Track’.”	50.00%					end
				end
	Reproduce results for each of the following approaches:	16.67%					end
	random	100.00%					end
	fair_lambdamart (Pairwise)	100.00%					end
	Deltr_gammas (Listwise fair LtR algorithm)	0.00%					end
	LM-relevance (LtR + randomization)	0.00%					end
	LM-rel-groups (LtR + external group definitions)	0.00%					end
	NLE_TEXT (controller)	0.00%					end
	NLE_META_PKL (Plackett-Luce sampler)	0.00%					end
	umd_relfair_ltr (Listwsise)	0.00%					end
	macewan_base (BM25)	0.00%					end
	QUARTZ (BM25 + group distribution score)	0.00%					end
	Terrier 2019	0.00%					end
	Terrier 2020	0.00%					end

	Describe individual approaches (write parallel with reproduction steps)	16.67%					end
	random	100.00%
	fair_lambdamart (Pairwise)	100.00%
	Deltr_gammas (Listwise fair LtR algorithm)	0.00%
	LM-relevance (LtR + randomization)	0.00%
	LM-rel-groups (LtR + external group definitions)	0.00%
	NLE_TEXT (controller)	0.00%
	NLE_META_PKL (Plackett-Luce sampler)	0.00%
	umd_relfair_ltr (Listwsise)	0.00%
	macewan_base (BM25)	0.00%
	QUARTZ (BM25 + group distribution score)	0.00%
	Terrier 2019	0.00%
	Terrier 2020	0.00%

	Design toy example	0.00%					end

	Write a couple paragraphs on why these approaches, how they were selected (methodology)	10.00%					end
	Write specific implementation details for each approach (appendix)	0.00%					end
	Write description dataset, indexing steps, any stemming etc (methodology)	0.00%					end
	Write down how the approaches performed on the dataset (experiments)	0.00%					end
				end
	Error analysis					end
	Determine how to perform error analysis on sequence of rankings – look at trec eval for inspiration?	0.00%					end
	Write 1-2 paragraphs on how to perform error analysis on a sequence of queries (methodology)	0.00%					end
				end
	Perform error analysis for each of the implemented approaches:	0.00%					end
	Term weighting (2020)	0.00%					end
	Plackett-Luce sampler (2020)	0.00%					end
	Controller (2020)	0.00%					end
	Data fusion (2020)	0.00%					end
	Pairwise LTR (2020)	0.00%					end
	Listwise LTR (2020)	0.00%					end
	Dissimilarity (2020)	0.00%					end
	Cost function (2020)	0.00%					end
	Pairwise LTR (2019)	0.00%					end
	Greedy algorithm (2019)	0.00%					end
	Diversification (2019)	0.00%					end
	Random shuffle (2019)	0.00%					end
	Term weighting (2019)	0.00%					end
				end
	Write error analysis section – discuss individual results and draw overarching conclusions to support the choice of improvement later	0.00%					end
				end
				end
				end
				end
	Propose improvement	0.00%					end
	Write literature review on causal fairness in ML as a whole	0.00%					end
	Write literature review on causal fairness in ranking specifically	0.00%					end
				end
	Based on literature and error analysis of previous years, propose a different ranking method that will hopefully work better	0.00%					end
				end
	Implement improvement	0.00%					end
	Implement code to create fair ranking	0.00%					end
	Write implementation details in appendix	0.00%					end
	Write idea behind implementation in its own section	0.00%					end
				end
	Evaluate improvement	0.00%					end
	Create runs with improved algorithm	0.00%					end
	Evaluate runs with 2019 & 2020 metrics	0.00%					end
	Do error analysis on improved runs	0.00%					end
				end
	Write discussion on error analysis and overall outcomes. Did our approach improve upon previous results? Can we explain why/why not? Do we propose remedies for what we see?	0.00%					end
				end
	Write the final version	0.00%					end
	Finish up drafts of methodology, experiments, etc.	0.00%					end
	Write background (all information that hasn’t been mentioned yet but is still relevant) draft	0.00%					end
	Write abstract draft	0.00%					end
	Write introduction draft	0.00%					end
	Write conclusion draft	0.00%					end

	Write background final	0.00%					end
	Write methodology final	0.00%					end
	Write experiments final	0.00%					end
	Write error analysis of previous approaches final	0.00%					end
	Write proposed improvement final	0.00%					end
	Write experiments proposed improvement final	0.00%					end
	Write error analysis proposed improvement final	0.00%					end
	Write discussion final	0.00%					end
	Write implementation details (appendix) final	0.00%					end
				end
	Write abstract final	0.00%					end
	Write introduction final	0.00%					end
	Write conclusion final	0.00%					end
				end
	Presentation	0.00%					end
	Whittle down thesis to the key ingredients	0.00%					end
	Pour the key ingredients into a presentation	0.00%					end
end	end	end	end	end	end	end	end	end	end	end