## Sheet1
[193 empty] | Green Light | [41 empty] | end
| SCHEDULE |  |  | planning |  |  | work | [6 empty] | work |  |  |  | winter break | [13 empty] | Kick off | [69 empty] | First stage review | [132 empty] | end
|  |  |  | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | end
| TASK | PROGRESS |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | end
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | end
| Start writing |  |  | 2022-07-25 31 end: end
| Create outline | 100% |  | 2022-07-25 31 end: end
end
| FairTrec 2021 & 2022 |  |  | 2022-07-25 31 end: end
| Read overview paper for Fairtrec 2021 | 100% |  | 2022-07-25 31 end: end
| Determine whether it makes sense to include approaches from fairtrec 2021 | 100% | bar: 2021-12-20 20 M
| Reproduce results |  |  | 2022-07-25 31 end: end
| Creating indexes |  |  | 2022-07-25 31 end: end
| Create Elasticsearch index as in ‘Fair Ranking in Academic Search’, by Malte Bonart | 100% |  | 2022-07-25 31 end: end
| Create Terrier index as in “McDonald and Ounis, ‘University of Glasgow Terrier Team at the TREC 2020Fair Ranking Track’.” | 50% |  | 2022-07-25 31 end: end
end
| Reproduce results for each of the following approaches: | 16.67% |  | 2022-07-25 31 end: end
| random | 100% |  | 2022-07-25 31 end: end
| fair_lambdamart (Pairwise) | 100% |  | 2022-07-25 31 end: end
| Deltr_gammas (Listwise fair LtR algorithm) | 80% |  | 2022-07-25 31 end: end
| LM-relevance (LtR + randomization) | 0% |  | 2022-07-25 31 end: end
| LM-rel-groups (LtR + external group definitions) | 0% |  | 2022-07-25 31 end: end
| NLE_TEXT (controller) | 0% |  | 2022-07-25 31 end: end
| NLE_META_PKL (Plackett-Luce sampler) | 0% |  | 2022-07-25 31 end: end
| umd_relfair_ltr (Listwsise) | 0% |  | 2022-07-25 31 end: end
| macewan_base (BM25) | 0% |  | 2022-07-25 31 end: end
| QUARTZ (BM25 + group distribution score) | 0% |  | 2022-07-25 31 end: end
| Terrier 2019 | 0% |  | 2022-07-25 31 end: end
| Terrier 2020 | 0% |  | 2022-07-25 31 end: end
| Describe individual approaches (write parallel with reproduction steps) | 16.67% |  | 2022-07-25 31 end: end
| random | 100%
| fair_lambdamart (Pairwise) | 100%
| Deltr_gammas (Listwise fair LtR algorithm) | 90%
| LM-relevance (LtR + randomization) | 0%
| LM-rel-groups (LtR + external group definitions) | 0%
| NLE_TEXT (controller) | 0%
| NLE_META_PKL (Plackett-Luce sampler) | 0%
| umd_relfair_ltr (Listwsise) | 0%
| macewan_base (BM25) | 0% | bar: 2021-12-20 20 M
| QUARTZ (BM25 + group distribution score) | 0%
| Terrier 2019 | 0%
| Terrier 2020 | 0% | bar: 2021-12-20 20 M
| First design toy example | 0% |  | 2022-07-25 31 end: end
| Write a couple paragraphs on why these approaches, how they were selected (methodology) | 10% |  | 2022-07-25 31 end: end
| Write specific implementation details for each approach (appendix) | 0% |  | 2022-07-25 31 end: end
| Write description dataset, indexing steps, any stemming etc (methodology) | 0% |  | 2022-07-25 31 end: end
| Write down how the approaches performed on the dataset (experiments) | 0% |  | 2022-07-25 31 end: end
end
| Error analysis |  |  | 2022-07-25 31 end: end
| Determine how to perform error analysis on sequence of rankings – look at trec eval for inspiration? | 0% |  | 2022-07-25 31 end: end
| Write 1-2 paragraphs on how to perform error analysis on a sequence of queries (methodology) | 0% |  | 2022-07-25 31 end: end
end
| Perform error analysis for each of the implemented approaches: | 0% |  | 2022-07-25 31 end: end
| Term weighting (2020) | 0% |  | 2022-07-25 31 end: end
| Plackett-Luce sampler (2020) | 0% |  | 2022-07-25 31 end: end
| Controller (2020) | 0% |  | 2022-07-25 31 end: end
| Data fusion (2020) | 0% |  | 2022-07-25 31 end: end
| Pairwise LTR (2020) | 0% |  | 2022-07-25 31 end: end
| Listwise LTR (2020) | 0% |  | 2022-07-25 31 end: end
| Dissimilarity (2020) | 0% |  | 2022-07-25 31 end: end
| Cost function (2020) | 0% |  | 2022-07-25 31 end: end
| Pairwise LTR (2019) | 0% |  | 2022-07-25 31 end: end
| Greedy algorithm (2019) | 0% |  | 2022-07-25 31 end: end
| Diversification (2019) | 0% |  | 2022-07-25 31 end: end
| Random shuffle (2019) | 0% |  | 2022-07-25 31 end: end
| Term weighting (2019) | 0% |  | 2022-07-25 31 end: end
end
| Write error analysis section – discuss individual results and draw overarching conclusions to support the choice of improvement later | 0% |  | 2022-07-25 31 end: end
end
end
end
end
| Propose improvement | 0% |  | 2022-07-25 31 end: end
| Write literature review on causal fairness in ML as a whole | 0% |  | 2022-07-25 31 end: end
| Write literature review on causal fairness in ranking specifically | 0% |  | 2022-07-25 31 end: end
end
| Based on literature and error analysis of previous years, propose a different ranking method that will hopefully work better | 0% |  | 2022-07-25 31 end: end
end
| Implement improvement | 0% |  | 2022-07-25 31 end: end
| Implement code to create fair ranking | 0% |  | 2022-07-25 31 end: end
| Write implementation details in appendix | 0% |  | 2022-07-25 31 end: end
| Write idea behind implementation in its own section | 0% |  | 2022-07-25 31 end: end
end
| Evaluate improvement | 0% |  | 2022-07-25 31 end: end
| Create runs with improved algorithm | 0% |  | 2022-07-25 31 end: end
| Evaluate runs with 2019 & 2020 metrics | 0% |  | 2022-07-25 31 end: end
| Do error analysis on improved runs | 0% |  | 2022-07-25 31 end: end
end
| Write discussion on error analysis and overall outcomes. Did our approach improve upon previous results? Can we explain why/why not? Do we propose remedies for what we see? | 0% |  | 2022-07-25 31 end: end
end
| Write the final version | 0% |  | 2022-07-25 31 end: end
| Finish up drafts of methodology, experiments, etc. | 0% |  | 2022-07-25 31 end: end
| Write background (all information that hasn’t been mentioned yet but is still relevant) draft | 0% |  | 2022-07-25 31 end: end
| Write abstract draft | 0% |  | 2022-07-25 31 end: end
| Write introduction draft | 0% |  | 2022-07-25 31 end: end
| Write conclusion draft | 0% |  | 2022-07-25 31 end: end
| Write background final | 0% |  | 2022-07-25 31 end: end
| Write methodology final | 0% |  | 2022-07-25 31 end: end
| Write experiments final | 0% |  | 2022-07-25 31 end: end
| Write error analysis of previous approaches final | 0% |  | 2022-07-25 31 end: end
| Write proposed improvement final | 0% |  | 2022-07-25 31 end: end
| Write experiments proposed improvement final | 0% |  | 2022-07-25 31 end: end
| Write error analysis proposed improvement final | 0% |  | 2022-07-25 31 end: end
| Write discussion final | 0% |  | 2022-07-25 31 end: end
| Write implementation details (appendix) final | 0% |  | 2022-07-25 31 end: end
end
| Write abstract final | 0% |  | 2022-07-25 31 end: end
| Write introduction final | 0% |  | 2022-07-25 31 end: end
| Write conclusion final | 0% |  | 2022-07-25 31 end: end
end
| Presentation | 0% |  | 2022-07-25 31 end: end
| Whittle down thesis to the key ingredients | 0% |  | 2022-07-25 31 end: end
| Pour the key ingredients into a presentation | 0% |  | 2022-07-25 31 end: end
end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end | end